## Internal Plan Master -Draft (hidden)
MAJOR TRANSPORT INFRASTRUCTURE AUTHORITY
MTIA Procurement Activity Plan
Forecasted Procurements FY 2020/2021 | [12 empty] | X | X | X
No. | Procurement name and description | Completed? | If not completed, Justification: | Estimated contract duration | Project Office | Estimated Contract Value | Methodology used to derive estimated contract value | Group/Business Unit | Procurement Contact details | Market Approach | Estimated date for market approach | Nature | Status | Tender ID | Comments
1 | ODG I&T: Reporting and Analytics: Technical Lead Consultant | ✓ |  | 12 Months |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
2 | ODG I&T: Reporting and Analytics: Delivery and Implementation Partner | ✓ |  | 12 Months |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
3 | MTIA Connect Program: Delivery Partner(s) (Panel) for implementation capability needed to deliver IT Strategy Implementation | ✗ | Put on hold due to Unifier taking precedence. | 3 Years |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
4 | MTIA Project Controls: External PCS Partner Delivery Partner, Phase 4 | ✓ |  | 9 Months |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
5 | MTIA Project Controls: Systems Integrator (SI) Implementation Phase 4 Release 1 and 2 | ✓ |  | 9 Months |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
6 | MTIA Project Controls: Support and licensing costs | ✓ |  | 12 Months |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services & Licences
7 | MTIA Project Controls: Project Controls Vendor Contract uplift | ✓ |  | 10 Years |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | TBD | Services
8 | MTIA I&T Operations: Audio / Visual room kit interfaces | ✗ | Put on hold | 1 Year |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services & Licences
9 | MTIA I&T Operations: Telephony integration with Microsoft Teams | ✗ | Put on hold | 1 Year |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services, Hardware & Licences
10 | MTIA I&T Operations: VPDSF implementation | ✓ |  | 2 Years |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services, Hardware & Licences
11 | MTIA I&T Operations: Service Desk Tool implementation | ✗ | Put on hold | 3 Years |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services, Licences
12 | Powercor impact assessment | ✓ |  | 1 Year |  |  | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | Standing Exemption | Q1 2020-2021 | Services
13 | Provision of Design & Upgrade Services | ✓ |  | 3 Years |  |  | Forecast usage/price | Communications & Stakeholder Relations | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q1 2020-2021 | Services
14 | Provision of Pipeline Impact Assessment for MAR | ✓ |  | 1 Year |  |  | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | Standing Exemption | Q1 2020-2021 | Services
15 | AusNet Assets Impacts Assessment for MAR | ✓ |  | 2 Years |  |  | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | Standing Exemption | Q1 2020-2021 | Services
16 | Provision of Electronic Data Room Services | ✗ | Postoned, expected to commence Q2 2021/22. | 3 Years |  |  | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2020-2021 | Services
17 | Information Exchange System | ✓ |  | 5 Years |  |  | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q1 2020-2021 | Services
18 | IT Hardware, Peripherals and Maintenance | ✓ |  | 5 Years |  |  | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2020-2021 | Services
19 | MTIA Service Desk System | ✓ |  | 5 Years |  |  | Market Analysis | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2020-2021 | Services
20 | Construction Related Services | ✗ | Deferred. | 5 Years |  |  | Historical Spend | Legal & Commercial | MRPV-Procurement@roadprojects.vic.gov.au | Panel/Register (non-SPC) | Q2 2020-2021 | Construction-related
21 | Provision of Medical Services | ✓ |  | 5 Years |  |  | Forecast usage/price | HR | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q3 2020-2021 | Services
22 | Hollow & VTWBC Monitoring | ✓ |  | 3 Years |  |  | Forecast usage/price | Echuca Moama Bridge Project | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2020-2021 | Construction-related
23 | Landscape Maintenance works | ✗ | Cancelled. | 3 Years |  |  | Forecast usage/price | Yan Yean Road Stage 1 Project | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2020-2021 | Construction-related
24 | Provision of Cleaning Services - RAN | ✗ | Postponed and about to get released. | 5 Years |  |  | Historical Spend | Industry Capability & Inclusion | LXRP-Procurement@levelcrossings.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2020-2021 | Services
25 | Millers Road Procurement/installation of noise mitigation | ✓ |  | 2 years |  |  | Forecast usage/price | Delivery | WGTP-Procurement@wgta.vic.gov.au | Construction Services Register | Q2 2020-2021 | Construction-related
26 | NELP Microsoft Surface 2 in one Computers | ✓ |  | 2.5 Years |  |  | Historical Spend | Corporate and governance | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2020-2021 | Services
27 | Constructability Advisory Services | ✓ |  | 6 Years |  |  | Historical Spend | Engineering | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (SPC) | Q1 2020-2021 | Goods
28 | Provision of Electronic Data Storage Services | ✗ | Contract extended with current supplier. | 6 Years |  |  | Historical Spend | Corporate and governance | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2020-2021 | Services
29 | Provision of Digital Asset Management System | ✓ |  | 5 Years |  |  | Market Analysis | Communications | MTIA-Procurement@mtia.vic.gov.au | RFP/RFQ/ITS (public) | Q1 2020-2021 | Services
30 | Advertising Buying Services | ✓ |  | 5 Years |  |  | Historical Spend | Communications | MTIA-Procurement@mtia.vic.gov.au | RFP (selective) | Q2 2020-2021 | Services
31 | VBB Education program - place-based | ✗ | Covid19 made team change direction- education program delivered online rather than in-person. | 1 Year |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
32 | Place-based event activation | ✓ |  | 1 Year |  |  | Market Analysis | Communications | MTIA-Procurement@mtia.vic.gov.au | RFP (selective) | Q3 2020-2021 | Services
33 | MTIA media training | ✓ |  | 5 Years |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au |  | Q2 2020-2021 | Services
34 | Print Management Services (Finsbury Green) | ✓ |  | 5 Years |  |  | Historical Spend | Communications | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services
35 | Photography | ✗ | Put on hold. | 3 Years |  |  | Historical Spend | Communications | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services
36 | MTIA Document Translation & Accessibility Services | ✓ |  | 3 Years |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services
37 | 3D Modelling and Data Visualisation | ✓ |  | 5 Years |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au | RFP (public) | Q1 2020-2021 | Services
38 | Customer Relationship Management system | ✗ | Put on hold. | 3 Years |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2020-2021 | Services
39 | MTIA funded project COVID-19 Testing Program | ✓ |  | 10 Weeks |  |  | Published pricing | Safety | MTIA-Procurement@mtia.vic.gov.au | TBD | Q1 2020-2021 | Services
40 | MTIA Safety Induction - Online Module including an 'Active Client' safety management training module | ✓ | Team is pursuing other options. | 6 Months |  |  | Forecast usage/price | Safety | MTIA-Procurement@mtia.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2020-2021 | Construction-related
41 | Technology enhancements to MTIA Core Safety Management System | ✗ | No longer required. | 6 Months |  |  | Historical Spend | Safety | MTIA-Procurement@mtia.vic.gov.au | Construction Services Register | Q3 2020-2021 | Services
42 | MTIA-wide panel of CALD specialty suppliers | ✗ | Terminated. | 3 Months |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au | RFQ | Q2 2020-2021 | Services
43 | EDRMS (Content Manager) Vendor Support Services | ✗ | Postponed to Jan 2022. | 3 Months |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBD | Q2 2020-2021 | Services
Forecasted Procurements FY 2021/2022
No. | Procurement name and description | Completed TBC | If not completed, Justification TBC | Estimated contract duration | Project Office | Estimated Contract Value | Methodology used to derive estimated contract value | Group/Business Unit | Procurement Contact details | Market Approach | Estimated date for market approach | Nature
44 | IT Technical Advisory Panel | N/A | N/A | 3 Years +1 Year + 1 Year | MRPV | TBA | Historical Spend | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-2022 | Services | New
45 | Tender Panel & Response Management System |  |  | 4 Years +2 Years + 2 Years | MRPV | TBA | Historical Spend | Commercial & Legal | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-2022 | Services | New
46 | Probity Auditor Services |  |  | 3 Years + 1 Year | MRPV | TBA | Historical Spend | Commercial & Legal | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021-2022 | Services | New
47 | Land Compensation & Advisory Panel |  |  | 3 Years + 1 Year | MRPV | TBA | Forecast usage/price | Land Planning | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (public) | Q3 2021-2022 | Services | New
48 | Better Connections |  |  | 1 Year | MRPV | TBA | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-2022 | Services | Not Started
49 | Creative Services Panel |  |  | 3 Years + 1 Year | MRPV | TBA | Historical Spend | Communications | MRPV-Procurement@roadprojects.vic.gov.au | RFP (selective) | Q2 2021-2022 | Services & Goods | Not Started
50 | Smart Workplace |  |  | 1 Year | MRPV | TBA | Historical Spend | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-2022 | Services | Not Started
51 | Geo-spatial Aerial Imagery |  |  | 3 Years + 1 Year + 1 Year | MRPV | TBA | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-2022 | Services | New
52 | Support & Maintenance services Audio Visual & Video Conference equipment |  |  | 1 Year + 1 Year + 1 Year | MRPV | TBA | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-2022 | Services & Goods | New
53 | Traffic Watch (integration of platform consolidating traffic data) |  |  | 1 Year | MRPV | TBA | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 / Q4 2021-2022 | Services | Not Started
54 | Partner Portal (integration of extra-net platform) |  |  | 1 Year | MRPV | TBA | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 / Q4 2021-2022 | Services
55 | Rail Operational Planning Advisory Services |  |  | 8 Years | RPV | 80000000 | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q3 2021 - 2022 | Construction Related Services | In Progress
56 | Alliance Facilitators |  |  | 4 Years | RPV | 2588320 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27480
57 | Legal Services |  |  | 4 Years | RPV | 15456000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021 - 2022 | Professional Advisory Services | In Progress | 27553
58 | Audio Visual Equipment and Maintenance Support Services |  |  | 3 Years | RPV | 240000 | Forecast usage/price | Finance & Administration | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021 - 2022 | ICT Goods and Services | In Progress | RFQ-2021-001
59 | Design Services for Pressure Reducing Stations (PRS) Relocation Works |  |  | 1 Year | RPV | 1125000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27790
60 | Quantity Surveying Services |  |  | 8 Years | RPV | 32000000 | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q3 2021 - 2022 | Construction Related Services | In Progress | 27146
61 | Design Services – Pipeline Alteration Works – Sunshine Station Upgrade Project |  |  | 2.5 Years | RPV | 1500000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27847
62 | Specialist Rail Planning and Strategic Services |  |  | 7 Years | RPV | 13420000 | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27618
63 | Technical Advisory Services |  |  | 8 Years | RPV | 720000000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q3 2021 - 2022 | Construction Related Services | In Progress | 27154
64 | Commercial and Financial Advisory Services |  |  | 8 Years | RPV | 80000000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021 - 2022 | Professional Advisory Services | In Progress | 27162
65 | Independent Environmental Audit |  |  | TBA | RPV | TBA | TBA | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | TBA | Q3 2021 - 2022 | Construction Related Services | Not Started
66 | Construction Works Panel |  |  | TBA | RPV | TBA | TBA | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | TBA | TBA | Construction Related Services | Not Started
67 | Independent Environmental Auditor |  |  | 6 years | NELP | 14000000 | Forecast usage/price | Project Controls | NELP-Procurement@northeastlink.vic.gov.au | Express of Interest (public) | Q4 2021-2022 | Construction-related | Not Started | N/A | N/A
68 | Air Quality Monitoring Equipment and Services |  |  | 6 years | NELP | 3300000 | Historical Spend | Land, Planning & Environment | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-2022 | Construction-related | New | 705 | In planning (MES in preparation and to be submitted for CPO approval within the next 2 weeks)
69 | Vegetation Management Panel |  |  | 6 years | NELP | 1100000 | Forecast usage/price | Land, Planning & Environment | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-2022 | Services | Not Started | 723 | In planning (Establishment of a panel for the provision of vegetation services)
70 | Audio Visual support services |  |  | 3-6 years | NELP | 400000 | Historical Spend | ITS | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-2022 | Services | New | 695 | In planning (Awaiting approval of MES from CPO)
71 | High Specification Computers |  |  | N/A | NELP | 250000 | Market Analysis | ITS | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-2022 | Goods | New | 727 | In planning
72 | MacBooks and iMacs |  |  | N/A | NELP | 240000 | Market Analysis | ITS | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-2022 | Goods | New | 703 | Tender Release and Market Interaction
73 | Contract Management Software |  |  | 6 years | NELP | 210000 | Historical Spend | Project Controls | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-2022 | Services | New | 667 | In planning
74 | Legal Services |  |  | < 1 year | NELP | 200000 | Forecast usage/price | Commercial & Legal | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021-2022 | Services | New | N/A | In planning
75 | Recruitment Services |  |  | < 1 year | NELP | 180000 | Historical Spend | People & Culture | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-2022 | Services | New | 710 | In planning
76 | Grants Management System |  |  | 3-6 years | NELP | 150000 | Market Analysis | Communications & Stakeholder Relations | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-2022 | Services | New | 732 | In planning
77 | Counselling Services |  |  | 6 years | NELP | 100000 | Forecast usage/price | Communications & Stakeholder Relations | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-2022 | Services | New | 726 | In planning
78 | MTIA Connect Program: Delivery Partner(s) (Panel) for implementation capability needed to deliver IT Strategy Implementation |  |  | 3 Years |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBA | Q3 / Q4 2021-2022 | Services
79 | MTIA I&T Operations: Audio / Visual room kit interfaces |  |  | 1 Year |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBA | Q3 / Q4 2021-2022 | Services
80 | MTIA I&T Operations: Telephony integration with Microsoft Teams |  |  | 1 Year |  |  | Forecast usage/price | IT | MTIA-Procurement@mtia.vic.gov.au | TBA | Q3 / Q4 2021-2022 | Services
81 | Rail Signalling Speciliast |  |  | 3 Years + 1 Year + 1 Year |  |  | Forecast usage/price | SST | MTIA-Procurement@mtia.vic.gov.au | TBA | Q2 2021-2022 | Services
81 | Pop-Up communicaty engagement panel |  |  | 3 Years + 1 Year + 1 Year |  |  | Forecast usage/price | Communications | MTIA-Procurement@mtia.vic.gov.au | TBA | Q3 / Q4 2021-2022 | Services
Note on M75: Likely to push out to Q1 or Q2 2022 - 2023

## FY2022-2023
MAJOR TRANSPORT INFRASTRUCTURE AUTHORITY
Procurement Activity Plan 2022-2023 |  | Updated 30/11/22
No. | Procurement name and description | Estimated contract duration | Group/Business Unit | Procurement Contact details* | Procurement Contact details | Market Approach | Estimated timing of market approach | Nature | Tender ID | Social Procurement
1 | Independent Environmental Auditor (Freeway Packages) | 6 years | Delivery - Freeways | NELP-Procurement@northeastlink.vic.gov.au | NELP-Procurement@northeastlink.vic.gov.au | RFP (public) | Q4 2022 | Construction-related
2 | Independent Financial Auditor (Freeway Packages) | 6 years | Delivery - Freeways | NELP-Procurement@northeastlink.vic.gov.au | NELP-Procurement@northeastlink.vic.gov.au | RFT/RFQ/ITS (SPC) | Q4 2022 | Services
3 | Venue Hire | 3 months | Delivery - Freeways | NELP-Procurement@northeastlink.vic.gov.au | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q4 2022 | Services
4 | Facility Management Service | 6 years | Finance & Business Services | NELP-Procurement@northeastlink.vic.gov.au | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q4 2022 | Services
5 | Vegetation Management Panel | 6 years | Land, Planning & Environment | NELP-Procurement@northeastlink.vic.gov.au | NELP-Procurement@northeastlink.vic.gov.au | RFT/RFQ/ITS (public) | Q1 2023 | Services
6 | Title Searching Services | 3 years | Land Planning & Environment | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q4 2022 | Services | tba
7 | Technical Advisory Services - construction-related | 3 years + 2 x 1-year options | Delivery | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q2 2023 | Services | tba
8 | Commercial Advisory Services | 3 years + 2 x 1-year options | Commercial & Legal | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q3 2023 | Services | tba
9 | Legal Advisory Services | 3 years + 2 x 1-year options | Commercial & Legal | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q3 2023 | Services | tba
10 | Transaction Advisory Services | 3 years + 2 x 1-year options | Delivery | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q3 2023 | Services | tba
11 | Cost Estimating Advisor | 3 years + 2 x 1-year options | Delivery | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q3 2023 | Services | tba
12 | Scheduling Advisory Services | 3 years + 2 x 1-year options | Delivery | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q3 2023 | Services | tba
13 | Drysdale Minor Civil Construction Services | 3 months | Program E | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q4 2022 | Construction | tba
14 | Commercial Office Removalist Services | 2 years | Finance & Corporate Services | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q4 2022 | Services | tba
15 | Video Conferencing Equipment & Services (Essendon Fields) | 2 years + 1-year option | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q4 2022 | Goods & Services | tba
16 | Thompsoms Road Shared Use Path works | 6 months | Program A | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (selective) | Q4 2022 | Construction | tba
17 | Scorecard - implementation and integration services for KPI reporting | 1 year | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q3 2023 | Goods & Services | tba
18 | Safe Assure - implementation and integration services for safety risk profile reporting | 6 months | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q3 2023 | Goods & Services | tba
19 | Ecologiq - implementation and integration services for monitoring data on recycled material | 1 year | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q4 2023 | Goods & Services | tba
20 | Site Assure Phase 2 - enhancements to existing solution | 6 months | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q2 2023 | Goods & Services | tba
21 | Image Hub - implementation of a portal for centralised storage | 1 year | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q1 2023 | Goods & Services | tba
22 | Utility Watch - implementation and development / proof of concept | 9 months | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q1 2023 | Goods & Services | tba
23 | Trusted Partner - implementation and development services | 1 year | IT | MRPV-Procurement@roadprojects.vic.gov.au | MRPV-Procurement@roadprojects.vic.gov.au | RFT/RFQ/ITS (SPC) | Q3 2023 | Goods & Services | tba
24 | Safety Services Panel - Leadership, Safety Culture Development and associated technical programs | 3 years | Safety | LXRP-Procurement@levelcrossings.vic.gov.au | LXRP-Procurement@levelcrossings.vic.gov.au | RFP (selective) | Q2 2023 | Services
25 | People and Culture Services Panel - Culture Development & Change, Capability and Skill development, Health and Wellbeing initiatives, Facilitation Services, and Team Building and Coaching. | 3 years | People and Culture | LXRP-Procurement@levelcrossings.vic.gov.au | LXRP-Procurement@levelcrossings.vic.gov.au | RFP (selective) | Q2 2023 | Services
26 | Videography - multiple contracts | 2 years | Communications | LXRP-Procurement@levelcrossings.vic.gov.au | LXRP-Procurement@levelcrossings.vic.gov.au | RFP (selective) | Q1 2023 | Services
27 | Indigenous Advisory Services - multiple contracts | 2 years | Business Strategy | LXRP-Procurement@levelcrossings.vic.gov.au | LXRP-Procurement@levelcrossings.vic.gov.au | RFP (selective) | Q4 2022 | Services
28 | Microsoft Viva Discovery and Implementation | 2 years | BST | LXRP-Procurement@levelcrossings.vic.gov.au | LXRP-Procurement@levelcrossings.vic.gov.au | RFP (selective) | Q4 2022 | Services
29 | Events Equipment Hire | 3 years | Communications | LXRP-Procurement@levelcrossings.vic.gov.au | LXRP-Procurement@levelcrossings.vic.gov.au | RFP (selective) | Q2 2023 | Services
30 | Provision of Mental Health First Aid training | 5 years | People and Inclusions | RPV-Procurement@railprojects.vic.gov.au | RPV-Procurement@railprojects.vic.gov.au | RFP (selective) | Q3 2023 | Services
31 | Provision of Coaching Services to Executives and Debriefing of Psychometric Inventories | 1 year | People and Inclusions | RPV-Procurement@railprojects.vic.gov.au | RPV-Procurement@railprojects.vic.gov.au | RFP (selective) | Q3 2023 | Services
32 | Provision of Constructability Advisory Services | 6 months | Development and Delivery | RPV-Procurement@railprojects.vic.gov.au | RPV-Procurement@railprojects.vic.gov.au | RFP (selective) | Q1 2023 | Services
33 | Provision of Advanced Presentation Skills Training | 1 year | People and Inclusions | RPV-Procurement@railprojects.vic.gov.au | RPV-Procurement@railprojects.vic.gov.au | RFP (selective) | Q2 2023 | Services
34 | Provision of Independent Environment Auditor Services | 5 years | Land, Planning & Environment | RPV-Procurement@railprojects.vic.gov.au | RPV-Procurement@railprojects.vic.gov.au | RFP (selective) | Q2 2023 | Services
35 | Workforce development | 1 year | Industrial Relations & Workforce Development |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (SPC) | Q1 2023 | Services
36 | Psychological health training modules - L&D training modules - online and face to face, mechanism for hosting, licenses | 5 years | Safety |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (selective) | Q2 2023 | Services
37 | Survey tool for psychological health assessment with consulting to develop survey | 5 years | Safety |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (selective) | Q1 2023 | Services
38 | Internal audit | 3 years | Integrity |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (SPC) | Q2 2024 | Services
39 | PowerBI Reporting Tools Development Services | 2 years | Signalling Strategy Taskforce |  | MTIA-Procurement@mtia.vic.gov.au | Panel/register (non-SPC) | Q2 2023 | Services
40 | Signalling Contract Legal Support Services - European Train Control System 1st Deployment | 2 years | ETCS 1st Deployment Project |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (selective) | Q3 2023 | Services
41 | Technical Advisor - European Train Control System 1st Deployment | 5 years | ETCS 1st Deployment Project |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (public) | Q3 2023 | Services
42 | Newport Rail Academy Modification Services | 2 years | Signalling Strategy Taskforce |  | MTIA-Procurement@mtia.vic.gov.au | RFT/RFQ/ITS (selective) | Q2 2023 | Services
43 | Signalling Standards Preparation & Review | 3 years | Signalling Strategy Taskforce |  | MTIA-Procurement@mtia.vic.gov.au | Panel/register (non-SPC) | Q3 2023 | Services
44 | Legal Services | 3 years | Commercial and Legal |  | WGTP-Procurement@wgta.vic.gov.au | RFT/RFQ/ITS (SPC) | Q1 2023 | Services | tba
45 | IT Assets Refresh | 2 years | Corporate Services |  | WGTP-Procurement@wgta.vic.gov.au | RFT/RFQ/ITS (SPC) | Q1 2023 | Goods & Services | tba

## Extra (hidden)
✓
✗

## 2021-22 Other Project Offices (hidden)
Response from other Project Offices:
WGTP planned procurement activities above $100K for 2020-21 will be via inter agency and SPC mandatory panel.
LXRP do not have any procurements planned that will be tendered to the open market.

## 2021-22 Internal Plan NELP (hidden)
MAJOR TRANSPORT INFRASTRUCTURE AUTHORITY
MTIA Procurement Activity Plan (Internal/External) 2021-2022
Note: Columns marked with X will NOT be included in the External plan |  |  | X | X | [6 empty] | X | X | X
No. | Procurement name and description | Estimated contract duration | Project Office | Estimated Contract Value | Methodology used to derive estimated contract value | Group/Business Unit | Procurement Contact details | Market Approach | Estimated date for market approach | Nature | Status | Tender ID | Comments
1 | Independent Environmental Auditor | 6 years | NELP | $14 m | Forecast usage/price | Project Controls | NELP-Procurement@northeastlink.vic.gov.au | Express of Interest (public) | Q4 2021-22* Likely to push out to Q1 or Q2 2022-23 | Construction-related | Not Started | N/A | N/A
2 | Air Quality Monitoring Equipment and Services | 6 years | NELP | $3.3 m | Historical Spend | Land, Planning & Environment | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-22 | Construction-related | New | 705 | In planning (MES in preparation and to be submitted for CPO approval within the next 2 weeks)
3 | Vegetation Management Panel | 6 years | NELP | $1.1 m | Forecast usage/price | Land, Planning & Environment | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-22 | Services | Not Started | 723 | In planning (Establishment of a panel for the provision of vegetation services)
4 | Audio Visual support services | 3-6 years | NELP | 400000 | Historical Spend | ITS | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-22 | Services | New | 695 | In planning (Awaiting approval of MES from CPO)
5 | High Specification Computers | N/A | NELP | 250000 | Market Analysis | ITS | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-22 | Goods | New | 727 | In planning
6 | MacBooks and iMacs | N/A | NELP | 240000 | Market Analysis | ITS | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-22 | Goods | New | 703 | Tender Release and Market Interaction
7 | Contract Management Software | 6 years | NELP | 210000 | Historical Spend | Project Controls | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-22 | Services | New | 667 | In planning
8 | Legal Services | < 1 year | NELP | 200000 | Forecast usage/price | Commercial & Legal | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021-22 | Services | New | N/A | In planning
9 | Recruitment Services | < 1 year | NELP | 180000 | Historical Spend | People & Culture | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-22 | Services | New | 710 | In planning
10 | Grants Management System | 3-6 years | NELP | 150000 | Market Analysis | Communications & Stakeholder Relations | NELP-Procurement@northeastlink.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021-22 | Services | New | 732 | In planning
11 | Counselling Services | 6 years | NELP | 100000 | Forecast usage/price | Communications & Stakeholder Relations | NELP-Procurement@northeastlink.vic.gov.au | RFP (selective) | Q2 2021-22 | Services | New | 726 | In planning
Note:
1. Financial estimates will not be included in the final public release and is for internal planning purposes only.
2. All planned procurement above $100k and above to be listed

## 2021-2 Internal Plan MRPV (hidden)
MAJOR TRANSPORT INFRASTRUCTURE AUTHORITY
MTIA Procurement Activity Plan (Internal/External) 2021-2022
Note: Columns marked with X will NOT be included in the External plan |  |  | X | X | [6 empty] | X | X | X
No. | Procurement name and description | Estimated contract duration | Project Office | Estimated Contract Value | Methodology used to derive estimated contract value | Group/Business Unit | Procurement Contact details | Market Approach | Estimated date for market approach | Nature | Status | Tender ID | Comments
1 | IT Technical Advisory Panel | 3 +1+1 | MRPV | tba | Historical Spend | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-22 | Services | New
2 | Tender Panel & Response Management System | 4 +2+2 | MRPV | tba | Historical Spend | Commercial & Legal | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-22 | Services | New
3 | Probity Auditor Services | 3 +1 | MRPV | tba | Historical Spend | Commercial & Legal | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021-22 | Services | New
4 | Land Compensation & Advisory Panel | 3 +1 | MRPV | tba | Forecast usage/price | Land Planning | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (public) | Q3 2021-22 | Services | New
5 | Better Connections | 1 | MRPV | tba | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-22 | Services | Not Started
6 | Creative Services Panel | 3 +1 | MRPV | tba | Historical Spend | Communications | MRPV-Procurement@roadprojects.vic.gov.au | RFP (selective) | Q2 2021-22 | Services & Goods | Not Started
7 | Smart Workplace | 1 | MRPV | tba | Historical Spend | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-22 | Services | Not Started
8 | Geo-spatial Aerial Imagery | 3 +1+1 | MRPV | tba | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-22 | Services | New
9 | Support & Maintenance services Audio Visual & Video Conference equipment | 1+1+1 | MRPV | tba | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q2 2021-22 | Services & Goods | New
10 | Traffic Watch (integration of platform consolidating traffic data) | 1 | MRPV | tba | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 / Q4 2021-22 | Services | Not Started
11 | Partner Portal (integration of extra-net platform) | 1 | MRPV | tba | Forecast usage/price | IT | MRPV-Procurement@roadprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 / Q4 2021-22 | Services
Note:
1. Financial estimates will not be included in the final public release and is for internal planning purposes only.
2. All planned procurement above $100k and above to be listed

## 2021-22 Internal Plan RPV (hidden)
MAJOR TRANSPORT INFRASTRUCTURE AUTHORITY
MTIA Procurement Activity Plan (Internal/External) 2021-2022
Note: Columns marked with X will NOT be included in the External plan |  |  | X | X | [6 empty] | X | X | X
No. | Procurement name and description | Estimated contract duration | Project Office | Estimated Contract Value | Methodology used to derive estimated contract value | Group/Business Unit | Procurement Contact details | Market Approach | Estimated date for market approach | Nature | Status | Tender ID | Comments
1 | Rail Operational Planning Advisory Services | 8 Years | RPV | 80000000 | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q3 2021 - 2022 | Construction Related Services | In Progress | TBC
2 | Alliance Facilitators | 4 Years | RPV | 2588320 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27480
3 | Legal Services | 4 Years | RPV | 15456000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021 - 2022 | Professional Advisory Services | In Progress | 27553
4 | Audio Visual Equipment and Maintenance Support Services | 3 Years | RPV | 240000 | Forecast usage/price | Finance & Administration | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021 - 2022 | ICT Goods and Services | In Progress | RFQ-2021-001
5 | Design Services for Pressure Reducing Stations (PRS) Relocation Works | 1 Year | RPV | 1125000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27790
6 | Quantity Surveying Services | 8 Years | RPV | 32000000 | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q3 2021 - 2022 | Construction Related Services | In Progress | 27146
7 | Design Services – Pipeline Alteration Works – Sunshine Station Upgrade Project | 2.5 Years | RPV | 1500000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (selective) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27847
8 | Specialist Rail Planning and Strategic Services | 7 Years | RPV | 13420000 | Forecast usage/price | Development & Delivery | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q2 2021 - 2022 | Construction Related Services | In Progress | 27618
9 | Technical Advisory Services | 8 Years | RPV | 720000000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP (public) | Q3 2021 - 2022 | Construction Related Services | In Progress | 27154
10 | Commercial and Financial Advisory Services | 8 Years | RPV | 80000000 | Forecast usage/price | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | RFP/RFQ/ITS (SPC) | Q3 2021 - 2022 | Professional Advisory Services | In Progress | 27162
11 | Independent Environmental Audit | TBC | RPV | TBC | TBC | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | TBC | Q3 2021 - 2022 | Construction Related Services | Not Started | TBC
12 | Construction Works Panel | TBC | RPV | TBC | TBC | Commercial & Legal | RPV-Procurement@railprojects.vic.gov.au | TBC | TBC | Construction Related Services | Not Started | TBC
Note:
1. Financial estimates will not be included in the final public release and is for internal planning purposes only.
2. All planned procurement above $100k and above to be listed

## Data List (hidden)
Methodology used to derive estimated contract value | Market Approach | Nature | Status | Project Office | Estimated date for market approach
Historical Spend | Construction Services Register | Goods | Not Started | LXRP | Q1 2020-2021
Market Analysis | Express of Interest (public) | Services | New | MRPV | Q2 2020-2021
Published pricing | Panel/Register (non-SPC) | Construction-related |  | NELP | Q3 2020-2021
Forecast usage/price | RFP (public) | Construction |  | ODG | Q4 2020-2021
| RFP (selective) |  |  | RPV
| RFP/RFQ/ITS (SPC) |  |  | WGTP
RFP/RFQ/ITS (public)
RFP/RFQ/ITS (selective)